## 2018 Review
REVIEW ASSY SYSTEM 2018
[15 empty] | Make system |  |  |  | Test plan |  |  |  | Apply plan
new | apply | kaizen & expand | fllow | SYSTEMS |  |  |  |  | Reference | TARGET | RESULT | PIC | Next plan
|  |  |  | I. System develop new 2018 | [8 empty] | Note | 2019-01-19 | 2019-02-19 | 2019-03-19 | 2019-04-19 | 2019-05-19 | 2019-06-19 | 2019-07-19 | 2019-08-19 | 2019-09-19 | 2019-10-19 | 2019-11-19 | 2019-12-19
1 | 1 |  |  | 1. Apply Camera Check program | [7 empty] | Thao
[5 empty] | 1 | ASSY 1 |  |  |  | Apply all | 100%
[5 empty] | 2 | ASSY 2 |  |  |  | Apply all | 70% |  | can apply all
1 | 1 |  |  | 2. Apply Media label printing System | [5 empty] | zero NG lable printting to line |  | Thao
[5 empty] | 2.1. Apply version 1 (copy from TL) | [5 empty] | 100%
[5 empty] | 2.2. Kaizen System (combine canon dat) |  |  |  | Combine with canon dat | reduce duplicate operator on lable printing & canon dat | 35% | bar: 2019-02-19 to 2019-03-19
1 | 1 |  |  | 3. Cut PI book control at workshop | [7 empty] | Thao
[5 empty] | 1 | ASSY 1 & ASSY 2 |  |  |  | cut PI book & katsujin 0.5 OP | 100%
[5 empty] | 3 | ASSY 3 & ASSY M |  |  |  | cut PI book | 0% |  | can apply all
1 | 1 |  |  | 4. Control PA
[5 empty] | 1 | Step 1: control in-out by System |  |  |  | cut excel file | 100% | Song
[5 empty] | 2 | Step 2: Auto caculate plan supply, replace order form, index control.. |  |  |  | stirckly control by system | 0% |  | wait ASSY make priority sys
1 | 1 |  |  | 5. PA Grease (cân mỡ LBP) | [7 empty] | Thao
[5 empty] | 2. winform |  |  |  |  | Katsujin 0.5 OP | 100%
1 |  |  |  | 6. Control in-out at Subpregnant (wait apply) | [7 empty] | Song
[5 empty] | 1 | step 1 |  |  |  | cut book control in-out | 50% |  | wait test
|  |  |  | 7. Big part production Kitting (PDC2) | [7 empty] | Thao
[5 empty] | 2. winform | [6 empty] | Thao
1 | 1 |  |  | 7. TSS & Production Auto machine
[5 empty] | 1 | Call TSS & sum chocote |  |  |  |  | 100%
[5 empty] | 2 | Production & progress |  |  |  |  | 60% | bar: 2019-01-19 to 2019-02-19
[5 empty] | 3 | Auto make plan |  |  |  |  | 0% | bar: 2019-03-19 to 2019-04-19
1 | 1 |  |  | 8. PM Maintenance Control (TPM System) | [5 empty] | Apply OK | 100% | Thao | wait ASSY request
new | apply | kaizen & expand | fllow | II. Fllow & kaizen Old System
9. Cellmanagement system
|  |  | 1 |  | 7.1. Attendance | [5 empty] | 1 | Thao | bar: 2019-03-19 to 2019-04-19
|  |  | 1 |  | 7.2. Mistake control | [5 empty] | 1 | Thao
|  | 1 |  |  | 7.3. TSS | [5 empty] | 1 | Song
1 | 1 |  |  |  | 7.4. Part visualize | [5 empty] | 1 | Song
|  |  | 1 |  | 7.5. Manpower | [5 empty] | 1 | Thao
|  | 1 |  |  | 7.6. uniform | [5 empty] | 1 | Thao
|  |  | 1 |  | 7.7. Changing point | [5 empty] | 1 | Thao
1 |  |  |  |  | 7.8. | Visualize QAFC |  |  |  |  | 1 | Thao
|  | 1 | 1 | 10. ESD System | [7 empty] | Thao,Song
[5 empty] | 8.1. web show | [5 empty] | 1 | Song
[5 empty] | 8.2. winform | [5 empty] | 1 | Thao
|  | 1 | 1 | 11. Check sheet less System | [7 empty] | Thao
[5 empty] | 1 | Apply new ST KMK check B32 & D39 |  |  |  |  | 1 | Thao
[5 empty] | 2 | Make master ZK,BM check BM,camera |  |  |  |  | 1 | Thao
[5 empty] | 3 | Modify checker D37,D83,E52,E53 |  |  |  |  | 1 | Thao
[5 empty] | 4 | Modify ZK B32,D39 add KMK |  |  |  |  | 1 | Thao
[5 empty] | 5 | Modify D37 |  |  |  |  | 1 | Thao
[5 empty] | 6 | Modify D83,E52,E53 |  |  |  |  | 1 | Thao
[5 empty] | 7 | Kaizen Check sheet less offline |  |  |  |  | 1 | Thao
[5 empty] | 8 | New model F23,24 (same E26,E27) | [5 empty] | Thao | bar: 2019-01-19
|  |  | 1 | 12.QAFC | [7 empty] | Thao
|  |  | 1 |  | 1 | Untighten (lực tháo) |  |  |  |  | 1 | Thao
|  |  | 1 |  | 2 | Tightem (lực bắt) |  |  |  |  | 1 | Thao
[5 empty] | 3 | Grease (cân mỡ) |  |  |  |  | 1 | Thao
|  | 1 | 1 | 13. LBP System | [7 empty] | Thao
[5 empty] | 1 | Production Counter |  |  |  |  | 1 | Thao
[5 empty] | 2 | A&I visualize
[5 empty] | 3 | Daily report |  |  |  |  | 1 | Thao
|  |  | 1 | 14. Quality System (winform) | [7 empty] | Thao
|  |  | 1 | 15. Spare part control (champ) | [7 empty] | Song
[6 empty] | Link to TPM system |  |  |  |  | 1 | Thao
|  |  | 1 | 16. Work standard system (webform) | [7 empty] | Thao
|  |  | 1 | 17. Batery control (PHP) | [7 empty] | Song
[7 empty] | Develop New | 10
[7 empty] | Trial & Apply | 8
[7 empty] | Kaizen & Expand | 5
[7 empty] | Fllow Old | 14

## 2019 Plan
PLAN ASSY SYSTEM 2019-v04
[14 empty] | Make system |  |  |  | Test plan |  |  |  | Apply plan
new | apply | kaizen &expand | Fllow old | SYSTEMS |  |  | PURPOSE |  | TARGET | STATUS | PIC | Next plan
|  |  |  | I. System develop new 2019 | [7 empty] | Note | 2019-01-19 | 2019-02-19 | 2019-03-19 | 2019-04-19 | 2019-05-19 | 2019-06-19 | 2019-07-19 | 2019-08-19 | 2019-09-19 | 2019-10-19 | 2019-11-19 | 2019-12-19
1 | 1 |  |  | 1. Apply Media label printing System | [6 empty] | Thao
[5 empty] | 1. Apply version 1 (copy from TL) |  |  |  |  | 100%
[5 empty] | 2. Kaizen System : control supply to cell |  | cut book record & exactly data all ASSY 1 + 2 |  | 100% | 0% | bar: 2019-10-19 to 2019-12-19
[5 empty] | 3 | Kaizen System (from QV) | No NG label supply to cell |  | 50% | 0% | bar: 2019-07-19 to 2019-08-19
1 | 1 |  |  | 2. Physical Inventory System | [6 empty] | Thao,Song
[5 empty] | 1 | Cut summarize book control | cut book control in-out |  | 100% | 70%
[5 empty] | 2 | Control in-out step 1: Sub pregnant & Auto machine |  |  | 100% | 50% |  | wait test | bar: 2019-04-19 to 2019-06-19
[5 empty] | 3 | Control in-out Step 2: expand all Assy areas | Control in-out by system - replace book |  | 100% |  | Song
[5 empty] | 4 | Link DSS, Lending part, In-Out System | exactly data |  | apply OK | 10%
[5 empty] | 5 | Sumarize data
1 | 1 |  |  | 3. Kitting Production PDC2 | [6 empty] | Thao
[5 empty] | 2. winform |  | Count actual production timely & prevent wrong part |  | E26E27 & Splow | 30% |  | not test | bar: 2019-04-19 to 2019-06-19
1 | 1 |  |  | 4. TSS & Production Auto machine | [6 empty] | Song
[5 empty] | 1 | Call TSS & sum chocote | Auto sum chocote & call TSS |  | 100% | 100%
[5 empty] | 2 | Production & progress | Visualize production & progress timly |  | 100 | 60% | bar: 2019-01-19 to 2019-02-19
[5 empty] | 3 | Auto make plan | Auto make plan for auto machine jig daily |  | 80% | 0%
1 | 1 |  |  | 5. Control PA
[5 empty] | 1 | Step 1: control in-out by System | cut excel file |  | finish | 100% | Song
[5 empty] | 2 | Step 2: Replace order form, index control.. | stirckly control by system |  | finish | 0%
1 | 1 |  |  | 6. Training System |  |  | Apply Training System for ASSY Dept |  | 80% | 0% | Song,Thao
[5 empty] | 1 | Analyse for ASSY Function |  |  |  |  | Thao
[5 empty] | 2 | Develop for ASSY Function |  |  |  |  | Song
new | apply | kaizen &expand | Fllow old | II. Fllow & kaizen Old System
7. Cellmanagement system
|  | 1 |  |  | 7.1. Attendance : add scan card OP at workshop |  | Correct data |  |  | 0% | Thao | bar: 2019-06-19 to 2019-08-19
|  |  | 1 |  | 7.2. Mistake control | [5 empty] | Thao
|  |  | 1 |  | 7.4. Part visualize | [5 empty] | Song
|  | 1 |  |  | 7.5. Manpower |  | Link to HR System -> cut time upload new man manual |  | finish | 0% | Thao | bar: 2019-07-19
|  |  | 1 |  | 7.6. uniform | [5 empty] | Thao
|  |  | 1 |  | 7.7. Changing point | [5 empty] | Thao
|  | 1 |  |  | 7.8. | Visualize QAFC | Expand visualize Grease & tighten force |  | finish |  | Thao | bar: 2019-08-19
|  |  | 1 | 8. ESD System | [6 empty] | Thao,Song
[5 empty] | 1 | ESD checking program | expand for 7 new jigs OK |  |  |  | Thao
[5 empty] | 2 | Visualize ESD on manpower |  |  |  |  | Song
|  |  | 1 | 9. TPM System | [6 empty] | Thao
[5 empty] | 1 | Kaizen function approve |  |  |  | 0% | Thao
[5 empty] | 2 | Kaizen function check history |  |  |  |  | Thao
|  | 1 | 1 | 10. Check sheet less System |  |  | no paper check sheet MP |  | finish |  | Thao
[5 empty] | 1 | Upload checker: change upload method | Fastly upload data + reducce Server performance |  | OK new model | 0% | Thao
[5 empty] | 2 | ZK | Cut scan reject at ZK station |  | finish | 0% | Thao
[5 empty] | 3 | INSIDE,BM | Add check Power supply & image for E52,E53,D83 at BM |  | finish | 0% | Thao | bar: 2019-04-19
[5 empty] | 4 | Camera check | Smoothly running & expand for new model 2019 OK |  | finish | 0% | Thao
[5 empty] | 5 | Apply new model E52,E53,D83 | Complete Expand for new model |  | finish | 30% | Thao | bar: 2019-01-19
[5 empty] | 6 | Apply new model F23,24 (same E26,E27) | Complete Expand for new model |  | finish | 0% | bar: 2019-02-19; 2019-05-19
|  |  |  | 11.QAFC | [6 empty] | Thao
|  |  | 1 |  | 1 | Untighten (lực tháo)
|  |  | 1 |  | 2 | Tightem (lực bắt)
|  |  | 1 |  | 3 | Grease (cân mỡ)
|  | 1 |  | 12. LBP System | [6 empty] | Thao
[5 empty] | 1 | Production Counter | Cut 10' daily SLD upload manual |  | finish | 0% | Thao | bar: 2019-02-19
[5 empty] | 2 | A&I visualize
[5 empty] | 3 | Daily report | Link correct OPR |  |  | 0 | Thao
|  |  | 1 | 13. Quality System (winform) | [6 empty] | Thao
[5 empty] | 1 | Kaizen funtion export for excell 2016 |  |  |  |  | Thao | bar: 2019-02-19
|  |  | 1 | 14. Spare part control (champ) | [6 empty] | Song
|  |  | 1 | 15. Work standard system (webform) | [6 empty] | Thao
|  |  | 1 | 16. Batery control (PHP) | [6 empty] | Song
|  |  | 1 | 17. TSS System | [6 empty] | Song
[8 empty] | 2019 | 2018
[7 empty] | Develop New | 6
[7 empty] | Trial & Apply | 6
[7 empty] | Kaizen & Expand | 5
[7 empty] | Fllow Old | 15

## 2018 Review (2)
REVIEW ASSY SYSTEM 2018
[13 empty] | Make system |  |  |  | Test plan |  |  |  | Apply plan
new | apply | kaizen & expand | fllow | SYSTEMS |  |  | PURPOSE | TARGET | RESULT | PIC | Next plan
|  |  |  | I. System develop new 2018 | [6 empty] | Note | 2019-01-19 | 2019-02-19 | 2019-03-19 | 2019-04-19 | 2019-05-19 | 2019-06-19 | 2019-07-19 | 2019-08-19 | 2019-09-19 | 2019-10-19 | 2019-11-19 | 2019-12-19
1 | 1 |  |  | 1. Camera Check program |  |  | - Keep history camera check - Prevent NG product to PK | Apply all ASSY 1+ ASSY 2 | done | Thao
1 | 1 |  |  | 2. Media label printing System |  |  | - Control history print lable - Prevent NG label to cell | Apply OK from TL | done | Thao
1 | 1 |  |  | 3. Physical Inventory System |  |  | - Reduce workload & Cut PI book - Exactly data & visualize index | - Cut book record PI data by cell - Reduce workload (0.5 OP) | Apply OK Assy 1+2 | Thao
1 | 1 |  |  | 4. Control PA |  |  | - Record in-out by System - Correct data & control strickly material | OK control in-out | Control in-out done | Song
1 | 1 |  |  | 5. IFC Grease (cân mỡ) |  |  | - Correct data & reduce workload - Visulize index | Apply OK | done | Thao
1 |  |  |  | 6. Control in-out at Subpregnant (wait apply) |  |  | - Control in-out at sub pregnant - Visualize index | Apply OK | remain test system | Song
|  |  |  | 7. Big part production Kitting (PDC2) | [5 empty] | Thao
1 | 1 |  |  | 7. TSS & Production Auto machine |  |  | - Count production Auto machine - Fastest call PM support | Apply OK | done | Song
1 | 1 |  |  | 8. PM Maintenance Control (TPM System) |  |  | - Auto make maintain schedule jig/tool - Keep history maintenace - warning & remind staff schedule | Apply OK | done | Thao | wait ASSY request
new | apply | kaizen & expand | fllow | II. Fllow & kaizen Old System
|  |  |  | 9. Cellmanagement system |  |  | - Show & visualize all information by cell: manpower, PI, attendance, ... - Reduce workload | Fllow System | continue | Thao
|  | 1 | 1 | 10. ESD System |  |  | - Quality upcheck ESD - Reduce workload CLD update OP card - Link to Cell management System | - Cut time CLD update OP card - Cut 2 PC for checking ESD | done | Thao,Song
|  | 1 | 1 | 11. Check sheet less System |  |  | - No check sheet paper on cell - Reduce workload - Correct data & quality up | - Expand & aplly for D33,D34,D37 - Auto up version, no trouble upload slowly - Apply offline program | done | Thao
|  |  | 1 | 12.QAFC |  |  | - Reduce workload & correct data - Visualize index | - Gather data all in one | done | Thao
|  | 1 | 1 | 13. LBP System |  |  | - Production timely - Correct data OPR & daily report | - Enough OPR data timely | done | Thao
|  |  | 1 | 14. Quality System (winform) |  |  | - Visualize & report exactly OPR IJ data | Fllow System | continue | Thao
|  |  | 1 | 15. Spare part control (champ) |  |  | - Control sparepart on stock | - Link TPM System | done | Song, Thao
|  |  | 1 | 16. Work standard system (webform) |  |  | - Control update work standard | Fllow System | continue | Thao
|  |  | 1 | 17. Batery control (PHP) |  |  | - Control batery & time batery charge | Fllow System | continue | Song
|  |  |  | 18. TSS System |  |  | - Unity stop time, visulize data | - New confirm stop time procedure | done | Song
Develop New
Trial & Apply
Kaizen & Expand
Fllow Old

## 2019 Plan (2)
PLAN ASSY SYSTEM 2019-v03
[13 empty] | Make system |  |  |  | Test plan |  |  |  | Apply plan
new | apply | kaizen &expand | Fllow old | SYSTEMS |  | PURPOSE |  | TARGET | STATUS | PIC | Next plan
|  |  |  | I. System develop new 2019 | [6 empty] | Note | 2019-01-19 | 2019-02-19 | 2019-03-19 | 2019-04-19 | 2019-05-19 | 2019-06-19 | 2019-07-19 | 2019-08-19 | 2019-09-19 | 2019-10-19 | 2019-11-19 | 2019-12-19
1 | 1 |  |  | 1. Media label printing System |  | - Control history print lable - Prevent NG label to cell |  | - Control supply, cut in-out book - Apply camera check label | 0% | Thao
1 | 1 |  |  | 2. Physical Inventory System |  | - Reduce workload & Cut PI book - Exactly data & visualize index |  | - Cut book control in-out & exactly data for sub preg, auto machine & PCB part | 0% | Thao, Song
1 | 1 |  |  | 3. Kitting Production PDC2 |  | - Count actual production timely - Prevent wrong part to cell |  | Apply for E26,E27 | 10% | Thao
1 | 1 |  |  | 4. TSS & Production Auto machine |  | - Count production Auto machine - Fastest call PM support |  | - Auto make plan, reduce workload for CLD | 0% | Song
1 | 1 |  |  | 5. Control PA |  | - Correct data & reduce workload - Visulize index |  | - Strickly control in-out | 0% | Song
1 | 1 |  |  | 6. Training System |  | - Record history training - Take test on System |  | - Apply from IT training system for ASSY | 0% | Song, Thao
new | apply | kaizen &expand | Fllow old | II. Fllow & kaizen Old System
|  |  |  | 7. Cellmanagement system |  | - Show & visualize all information by cell: manpower, PI, attendance, ... - Reduce workload |  | - Add OP scan card on cell for attendance system check - Link to HR System -> cut time upload new man manual | 0% | Thao
|  |  | 1 | 8. ESD System |  | - Quality upcheck ESD - Reduce workload CLD update OP card - Link to Cell management System |  | - Expand funtion repalce scan card on cell | 0% | Thao,Song
|  |  | 1 | 9. TPM System |  | - Auto make maintain schedule jig/tool - Keep history maintenace - warning & remind staff schedule |  | Fllow system |  | Thao
|  | 1 | 1 | 10. Check sheet less System |  | - No check sheet paper on cell - Reduce workload - Correct data & quality up |  | - Expand & apply for new model: E52,E53,D83 & F23,F24 - Reduce setup time & reduce operator using system - Fastest upload data -> reduce server performance | 0% | Thao
|  |  |  | 11.QAFC |  | - Reduce workload & correct data - Visualize index |  | Fllow system |  | Thao
|  | 1 |  | 12. LBP System |  | - Production timely - Correct data OPR & daily report |  | - Correct production timely - Cut 10' daily SLD upload manual | 0% | Thao
|  |  | 1 | 13. Quality System (winform) |  | - Visualize & report exactly OPR IJ data |  | Fllow system |  | Thao
|  |  | 1 | 14. Spare part control (champ) |  | - Control sparepart on stock |  | Fllow system |  | Song
|  |  | 1 | 15. Work standard system (webform) |  | - Control update work standard |  | Fllow system |  | Thao
|  |  | 1 | 16. Batery control (PHP) |  | - Control batery & time batery charge |  | Fllow system |  | Song
[7 empty] | 2019 | 2018
[6 empty] | Develop New | 6
[6 empty] | Trial & Apply | 6
[6 empty] | Kaizen & Expand | 2
[6 empty] | Fllow Old | 7