## Sheet1
REVIEW ASSY SYSTEM 2018
[9 empty] | Make system |  |  |  | Test plan |  |  |  | Apply plan
SYSTEMS |  |  | Reference | TARGET | RESULT | PIC | Next plan
I. System develop new 2018 | [6 empty] | Note | 2019-01-19 | 2019-02-19 | 2019-03-19 | 2019-04-19 | 2019-05-19 | 2019-06-19 | 2019-07-19 | 2019-08-19 | 2019-09-19 | 2019-10-19 | 2019-11-19 | 2019-12-19
1. Apply Camera Check program | [5 empty] | Thao
| 1 | ASSY 1 |  | Apply all | 100%
| 2 | ASSY 2 |  | Apply all | 70% |  | can apply all
2. Apply Media label printing System |  |  |  | zero NG lable printting to line |  | Thao
| 2.1. Apply version 1 (copy from TL) |  |  |  | 100%
| 2.2. Kaizen System (combine canon dat) |  | Combine with canon dat | reduce duplicate operator on lable printing & canon dat | 35% | bar: 2019-02-19 to 2019-03-19
3. Cut PI book control at workshop | [5 empty] | Thao
| 1 | ASSY 1 & ASSY 2 |  | cut PI book & katsujin 0.5 OP | 100%
| 3 | ASSY 3 & ASSY M |  | cut PI book | 0% |  | can apply all
4. Control PA
| 1 | Step 1: control in-out by System |  | cut excel file | 100% | Song
| 2 | Step 2: Auto caculate plan supply, replace order form, index control.. |  | stirckly control by system | 0% |  | wait ASSY make priority sys
5. PA Grease (cân mỡ LBP) | [5 empty] | Thao
| 2. winform |  |  | Katsujin 0.5 OP | 100%
6. Control in-out at Subpregnant (wait apply) | [5 empty] | Song
| 1 | step 1 |  | cut book control in-out | 50% |  | wait test
7. Big part production Kitting (PDC2) | [5 empty] | Thao
| 2. winform |  |  |  |  | Thao
7. TSS & Production Auto machine
| 1 | Call TSS & sum chocote |  |  | 100%
| 2 | Production & progress |  |  | 60% | bar: 2019-01-19 to 2019-02-19
| 3 | Auto make plan |  |  | 0% | bar: 2019-03-19 to 2019-04-19
8. Training System |  |  |  |  | 0% |  | wait ASSY request
II. Fllow & kaizen Old System
9. Cellmanagement system
| 7.1. Attendance |  |  |  | 1 | Thao | bar: 2019-03-19 to 2019-04-19
| 7.2. Mistake control |  |  |  | 1 | Thao
| 7.3. TSS |  |  |  | 1 | Song
| 7.4. Part visualize |  |  |  | 1 | Song
| 7.5. Manpower |  |  |  | 1 | Thao
| 7.6. uniform |  |  |  | 1 | Thao
| 7.7. Changing point |  |  |  | 1 | Thao
| 7.8. | Visualize QAFC |  |  | 1 | Thao
10. ESD System | [5 empty] | Thao,Song
| 8.1. web show |  |  |  | 1 | Song
| 8.2. winform |  |  |  | 1 | Thao
11. TPM System | [5 empty] | Thao
| 1 | Add function auto warning make schedule NG & miss maintain |  |  | 1 | Thao
12. Check sheet less System | [5 empty] | Thao
| 1 | Apply new ST KMK check B32 & D39 |  |  | 1 | Thao
| 2 | Make master ZK,BM check BM,camera |  |  | 1 | Thao
| 3 | Modify checker D37,D83,E52,E53 |  |  | 1 | Thao
| 4 | Modify ZK B32,D39 add KMK |  |  | 1 | Thao
| 5 | Modify D37 |  |  | 1 | Thao
| 6 | Modify D83,E52,E53 |  |  | 1 | Thao
| 7 | Kaizen Check sheet less offline |  |  | 1 | Thao
| 8 | New model F23,24 (same E26,E27) |  |  |  | Thao | bar: 2019-01-19
13.QAFC | [5 empty] | Thao
| 1 | Untighten (lực tháo) |  |  | 1 | Thao
| 2 | Tightem (lực bắt) |  |  | 1 | Thao
| 3 | Grease (cân mỡ) |  |  | 1 | Thao
14. LBP System | [5 empty] | Thao
| 1 | A&I visualize |  |  | 1 | Thao
| 2 | Daily report |  |  | 1 | Thao
15. Quality System (winform) | [5 empty] | Thao
16. Spare part control (champ) | [5 empty] | Song
|  | Link to TPM system |  |  | 1
17. Work standard system (webform) | [5 empty] | Thao
18. Batery control (PHP) | [5 empty] | Song