## Sheet1
ALL SYSTEM IN 2018
Name: | Đinh Văn Song
Code: | 827999
Department: | TS-PIT
JOB |  | Target | RESULT | NOTE | PLAN
I. New System | 1. PA | Step 1:Control In-out-Stock of Assy(Finish) replace excel file to No data loss Finish all function of this system(finish step 2) Cut manipulation of OP+ manipulation of shift leader Cut paper Mainline used to confirm,Automatic caculate amount of use Apply to the assy area | Finish step 1 Control In-Out-Stock of Assy replace excel file to No data loss | Delay step 2 for Auto production first | Start: 10/4/2018 End: 3/7/2018
| 2. Sub Pregnant | Finish all function of this system - Controll history In-Out-Stock Part - Cut off history on paper to No data loss - Improve check ability, accuracy (what’s KPI, for which report …) - Reduce time to record In-out part between MC & SP - Support to reduce manpower (total per year) - Support to reduce workload (total hour per year) - 79500 hour per year - Support to reduce cost (total $ per year) - Cost down book to control In-Out 500$ | 80% Waiting test+Apply |  | Start: 4/9/2018 End: 1/11/2018
| 3. AUTO | + TSS - Call PM repair - Save History repair + Production Visualize - Visualize immediate production for MANAGER - Automatic calculate Qty for machine - cut 4 day/month of leader | Step 1: Finish + TSS - Call PM repair - Save History repair + Production - Visualize immediate production for MANAGER | Waiting Analysis Step2 | Start: 2/11/2018 End: Now
II. Maintain System | 1. Cell Management | + Maintain+Kaizen TSS at Main Line + KaiZen part visualize | Continue |  | Start: 4/7/2018 End: 3/9/2018
| 2. ESD | +Kaizen and Maintain,Make new fucntion confirm and save history | Continue
| 3. PA Grease | Maintain,Upload new version and fix problem on system | Continue
| 4. Spare Part | Fix Problem and Maintain system | Continue
| 5. Battery(PHP) | +Kaizen ALL Department to 1 System | Finish at ASSY | Wating for PDC+LOG
| 6. Label printing | +Kaizen Input for system | Finish | Thao san continue make system